## Sheet1
Remarks
| 1. When “top side” and “Bottom side” are clicked on the stencil side then options should have the popup for the below options. Epocoat, Film plots, Spin plate, Inspection template, FG Material. Please refer the attached popup.png.. any suggestions? | Priority
| 2. (Master list of holidays should be automated, right now it requires us to enter it manually every year. We only have a few holidays that is observed here at Beam On. There should be a way it manually adds it by the holiday name and checking with the US calendar.) | After Launch
| 3. Delivered - email confirmation is not working. | Priority
| 4. On Hold Email – Need email alert for “ON HOLD”, “SHIPPED”, “DELIVERED”, “CANCELLED” | Priority
Current in (Progress) | 5. PO Missing email – need email alert for “PO Missing” | Priority
| 6. Email confirmation - Social networking signature links are not working. | Priority
| 7. At back end- when we open new tab, just show the order form. No need to show the menu | After Launch
| 8. Back end – edit- we should be able to edit the stencil side. | Priority
| 9. Customer screen – My orders- order status – need sort option for status | After Launch
| 10. Leading edge- please remove the character restriction. I think now it allows only 5 characters set-20 | After Launch
| 11. Stepdown- holiday to be considered. Expedite working correctly | Priority
| 12. Customer screen- Bottom banner- need to be editable from back end | Priority
| 13. Customer screen- status will be not shown for internal orders. | Priority
| 14. Customer screen – Data for Approval- need to open the pop up | Priority
Paul | 1. "Data for approval" was supposed to have a text popup or something to discourage it's usage. Actual language was given. Is it still being worked on? (Anh) - It is in progress. Already taken care of. | Priority
| 2. For stepdown I would prefer a check box under base thickness that doesn't show these buttons until checked. Otherwise it seems we are prompting customer to use stepdown | Priority
| 3. FG material will now be "DatumTension" | Pls Advise
| 4. I think a promotion text at the top where customer gets 15% discount off the stencil order on the 10th or 15th order would be good. And it will say "If you place 5 more orders your 5th stencil is 15% off !" This promotion will not work if Beam On has to make the order since it requires their login. | Pls Advise
Anh | 1. Admin Page - List of Order needs to refresh automatically like WIMS. Currently it does not. | Priority
| From what Trey and I had discussed this function will be developed after BOOTS2 has been launched and it will be a minor revision. - Anh N. 2. Admin Page - Company master list needs a Beam On Spec field. This in turn will apply to all engineers who are under that company if user chooses to or choose specific engineers from the drop down box (user is able to hold shift+ click to click multiple engineers as an option to apply. However if there are particular engineer who needs a custom spec? It can be changed from the masterlist engineer profiles and that will take precedance over the generic spec for the company. Example, Under Company Master list for Company 'A' Beam On spec field has been modified, once submitted pop up will ask if admin user would like to apply to all. Other option would be a drop down menu with ability to hold shift to highlight certain engineers and submit the change. | After Lainch
| 3. Admin Page - Phone # Format should be automatically formated as such + Country Code (area code)-phone-number (ex - +1 408-982-0161, +1 408-982-0161 x15) when user enters phone number. | Priority
| 4. Entry format for Address should also be standard. If the user enters the lets say a city name as santa clara? It should automatically notate it as Santa Clara. The first letter of the string should be capatilized and the first letter of the second string needs to be capitalized. | After Lainch
| 5. Bug: PO has no character restriction. I can enter infinite amount of characters and it will display it out of the screen. Please adjust to 16 characters for now (includes: numbers and letters). Once user clicks on PO # button and enter remove 'PO#' to have more flexability in formating it inside the button. | Priority
| 6. E-mail confirmations not working, tried creating new order under my alias and e-mail address. | Priority
| 7. Order Date/Due Date - Please add a Time Stamp in addition to the Date needs to be formated as such MM/DD/YYYY | ?
| 8. Bug: The 1000 character counter under "Special Instructions" does not reflect accuratly when the user applies the defaults from the profile. It doesn't negate the characters that are left for the user(s) to enter. | once we start to type then it calculates
| 9. Bug: Clear form doesn't clear the "Special Instructions" | After Launch
Trey | 1. Does not work in my internet Explorer. | Priority
(Anh) This doesn't work due to the compatability view for Internet Explorer. This feature was set, since current BOOTS does not work well with current Web Browsers. Once BOOTS2 is launched? There will be no problems ordering. Please turn off Compatability view to test further.
| 2. Apple, safari . The expedite charge does not work when you un-select the current date. ( It still displays the expedite charge. ) | Priority
| 3. Apple safari, Some foil thicknesses have a underscore under them | Priority
| 4. We must talk with Rajoo as to when the 40% charge will be applied. Right now a 6pm order with a 8 am delivery has no expedite charge. | working on it
| 5. Universal button for the boarder should be changed to something that specifies a default for the company in the special instructions. Example: Axiom boarder. The button should denote that we will use whatever is specified in the beam on specs and in the beam on specs we will have the axiom border. | Priority
| 6. Stepdown thicknesses are allowed to be incorrect. Example, I can have a 5 mil step down to 8 mil and then double stepped to 7mil. | it will show error when you click submit
| 7. Data upload, I noticed this is mandatory to submit the order. If so we need a spot to click to allow customer to enter old REF# or something so they can submit without upload. | Pls advise
Jeff
Alan
Rajesh
Brenda | Missing from frame sizes are 29x29x1 and 12x17 (Stanford Research uses this frame) (Anh) - The Custom size text box will be utilized for this purpose.
Rajoo

## Sheet2
1. When “top side” and “Bottom side” are clicked on the stencil side then options should have the popup for the below options. Epocoat, Film plots, Spin plate, Inspection template, FG Material. Please refer the attached popup.png.. any suggestions?
2. (Master list of holidays should be automated, right now it requires us to enter it manually every year. We only have a few holidays that is observed here at Beam On. There should be a way it manually adds it by the holiday name and checking with the US calendar.)
3. Delivered - email confirmation is not working.
4. On Hold Email – Need email alert for “ON HOLD”, “SHIPPED”, “DELIVERED”, “CANCELLED”
5. PO Missing email – need email alert for “PO Missing”
6. Email confirmation - Social networking signature links are not working.
7. At back end- when we open new tab, just show the order form. No need to show the menu
8. Back end – edit- we should be able to edit the stencil side.
9. Customer screen – My orders- order status – need sort option for status
10. Leading edge- please remove the character restriction. I think now it allows only 5 characters set-20
11. Stepdown- holiday to be considered. Expedite working correctly
12. Customer screen- Bottom banner- need to be editable from back end
13. Customer screen- status will be not shown for internal orders.
14. Customer screen – Data for Approval- need to open the pop up